## التقويم
سبتمبر
| 2022 |  | Mahedy Hasan | Engineer/ |  | شهر التقويم | سبتمبر
[6 empty] | سنة التقويم | 2022
[6 empty] | أول يوم من الأسبوع | الثلاثاء
| 44796 | 44797 | 44798 | 44799 | 44800 | 44801 | 44802
| 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05
الملاحظات اليومية | 2022-09-03: PEC Desgin updating ,photo add and other page design; 2022-09-04: Client app Developmet and make scratch and report for pakistani App developer team also web developer team; 2022-09-05: Client app Developmet and make scratch and report for pakistani App developer team also web developer team
| 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12
الملاحظات اليومية | Google analytical integration and PEC isuess and tmakan isuess | Backend panel setup of the web portal | Make API for Mobile App |  | Make access token for Mobile App(passport) | Sahwa Design start | Main page Design
| 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19
الملاحظات اليومية | Reqest form configure and git,cpanel godaddy isuess upload Sahwa website in sahwa ,new error isuess | Clients webportal Backend set for PEC | dashboard design |  | add employee and manager | department, team making | Onpage SEO and google analytical configure for Tamakan ,pec,sahwa
| 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26
الملاحظات اليومية | Team section | PEC,Sahwa,Tamakan Tracking section and Clients app integration | team assign |  | team assign | team manage | Car finder app
| 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03
الملاحظات اليومية | login page setup | admin panel step up | category add and product page design |  | product manage | Product searching | Making API
| 2022-10-04 | 2022-10-05
الملاحظات اليومية | 2022-09-27: Making API